# Terms of Reference (ToR)

Senior National Consultant to Support Preparation of the Country Programme Document (CPD)

### 1. Background

The Government of Lao PDR is preparing its Country Programme Document (CPD) under Phase Three (2025–2031) of the Enhanced Integrated Framework (EIF), which supports Least Developed Countries (LDCs) in advancing trade-led growth and integration into the global economy.

The CPD will serve as a nationally owned, up to five-year strategic framework that identifies Laos’s trade and investment priorities, proposed interventions, and implementation arrangements, aligned with national development strategies and MOIC Five Year Plan.

The CPD is co-created with the EIF partnership as a national priority trade programme - serving first and foremost as a platform to engage all partners, coordinate and mobilize resources, and as a catalytic vehicle for accessing EIF funding. It is anchored in the national Prioritized Action Matrix (PAM) on industry and trade-related technical assistance, which provides the baseline for partner alignment, sequencing, and progress measurement, while also acting as a lever to mobilize broader Aid for Trade resources.

Building on existing analyses, strategies, and lessons from earlier EIF phases, the CPD will provide a coherent and coordinated framework for trade-related development support in Lao PDR along with MOIC Five Year Plan for 2026-2030.

To support this process, the MOIC/PSO/ NIU intends to engage a qualified consultant (or team of consultants) to facilitate consultations, coordinate technical inputs, and draft the CPD and its annexes in line with EIF Phase 3 guidelines.

### 2. Objective of the Assignment

The objective of this consultancy is to support the preparation of a high-quality, evidence-based and nationally endorsed CPD that:

- Reflects Laos’ trade and investment priorities;

- Is anchored in the Prioritized Action Matrix (PAM) and aligned with EIF Phase Three guidelines; and

- Serves as a strategic framework for partner engagement and resource mobilization.

### 3. Scope of Work / Key Tasks

The consultant will work closely with the NIU, EIF Focal Point, relevant ministries and stakeholders, and may include the following tasks:

(i) Review and Analysis

- Review national and sectoral strategies, trade diagnostics, and relevant policy documents and outcomes and lessons from past EIF projects.

- Map ongoing and planned trade and investment-related initiatives to inform the PAM.

- Identify key trade priorities, challenges and opportunities for inclusion in the CPD.

(ii) Stakeholder Consultations

- Support the design and facilitation of consultative meetings and workshops with key stakeholders (government, private sector, development partners, and civil society).

- Document key outcomes and build consensus on priority areas and PAM actions.

- Ensure consultations feed directly into the draft CPD structure and content.

(iii) Drafting of the CPD and PAM

- Prepare the draft CPD in line with the EIF Phase Three CPD Template, ensuring the PAM is clearly developed and integrated as the central programming tool.

- Populate the required annexes (logframe, budget, risk matrix, stakeholder summary etc.).

- Incorporate comments from the NIU, EIF Executive Secretariat (ES), and Trust Fund Manager (TFM).

- Finalize the CPD for endorsement through a national validation workshop/meeting.

(iv) Technical Support and Coordination

- Provide technical advice to ensure coherence and alignment with national plans and EIF guidelines.

- Support translation, validation, and submission processes as needed.

Matrix of Responsibilities

| Ministry of Industry and Commerce (MOIC) | Consultant | EIF Executive Secretariat & Trust Fund Manager |
| --- | --- | --- |
| - Set the priorities using PAM - Ensure synergies and avoid duplication (mapping\outreach to key stakeholders) - Guide consultant on internal Ministry capacity and preferences on implementation modalities - Overall ownership of the CPD formulation process and the validation through National Steering Committee | - Drafting PAM and CPD with guidance from MOC and following templates and guidance issues by EIF - Supporting MOIC in outreach and consultation with key stakeholders - Understand and outline implementation modality preferences and assumptions in the CPD - Co-lead presentation of CPD draft to stakeholders and ultimately to National Steering Committee - Revise CPD as needed based on inputs from key stakeholders as identified by MOIC | - Issue guidelines and guidance on Phase 3 - Receive and review draft CPD and provide suggestions - Provide insights from historical analysis with a view to leveraging best practices and using lessons learned to inform assumptions, especially implementation modalities - Appraisal of formal CPD submission - Handling legal matters for the formalization of CPD with MIE’s after EIF Board approval |

4. Deliverables and Timeline

| Deliverable | Indicative Timeline |
| --- | --- |
| Inception report and workplan | Mid of January, 2026 |
| Draft PAM & Summary of stakeholder consultations | End of January, 2026 |
| Draft CPD (with annexes) | End of February, 2026 |
| Final validated CPD | End of March 2026 |

### 5. Reporting and Supervision

The consultant will work under the supervision of the National EIF Focal Point/NIU Coordinator, in close coordination with the other team members from the NIU and EIF Executive Secretariat and Trust Fund Manager. Regular virtual will be held to review progress and validate intermediate outputs.

### 6. Required Qualifications and Experience

- Advanced university degree in economics, trade, development, or related field.

- At least 7 years of experience in trade and development policy, project formulation, or Aid for Trade programming.

- Proven experience facilitating multi-stakeholder consultations and preparing strategic or programmatic documents.

- Strong analytical, writing, and communication skills.

- Familiarity with EIF processes, LDC contexts, and donor coordination frameworks is an asset.

- Fluency in English (spoken and written).

### 7. Duration and Level of Effort

The consultancy is expected to last 05 months, with an estimated 20 days of inputs.

### 8. Payment Schedule

Payments will be made upon submission and acceptance of deliverables in line with national or implementing partner procurement rules.

| Deliverable | % Payment |
| --- | --- |
| CPD draft outline / workplan | 20% |
| CPD draft document & obtaining inputs from key stakeholders | 40% |
| Final CPD and validation for submission | 40% |